REVISED COMMERCIAL PROPOSAL

# KLIYA MVP INTEGRATION & TECHNICAL SUPPORT

Prepared by Daybreak Tech-Innovations (Pty) Ltd

━━━━━━━━━━━━━━━━━━━━━━━━━━━━

| CLIENT | Kliya / [Client legal entity] |
| --- | --- |
| PROPOSAL REFERENCE | DB-KLIYA-MVP-REV2-110926 |
| ISSUE DATE | 11 September 2026 |
| VALID UNTIL | 25 September 2026 |
| PROJECT INVESTMENT | R230,000 fixed project fee (VAT only if applicable) |
| ESTIMATED EFFORT | Approximately 209 engineering hours at R1,100/hour |
| ESTIMATED DELIVERY | 8–10 weeks of active delivery, subject to client/vendor access |

# 1. Executive Summary

This revised proposal responds to Kliya’s founder-issued MVP Integration & Technical Support Brief. Daybreak’s role is to implement, validate and harden selected third-party integrations around the existing Kliya MVP. The core product build, product flows and visual system are not included.

The engagement is structured as a modular integration programme: approved providers are connected through a maintainable backend/API layer, external outputs are mapped into Kliya’s internal structures, failure states are handled gracefully, and the final implementation is documented for future maintenance or provider replacement.

COMMERCIAL BASIS The revised scope is estimated at approximately 209 engineering hours at Daybreak’s standard R1,100/hour rate, giving an estimated labour basis of R229,900. The commercial project fee is fixed at R230,000. The hours are planning estimates mapped to the approved workstreams; the engagement is priced for delivery of the agreed scope and outcomes, not for consuming an arbitrary block of hours.

# 2. Scope of Work

Implement approved third-party APIs/SDKs into the existing Kliya MVP.

Build and harden the backend/API layer required for each approved integration.

Map provider inputs and outputs into Kliya’s internal data structures.

Implement authentication, secure secret handling, request/response orchestration, retries, rate-limit handling, logging and graceful failure states where appropriate.

Test end-to-end data flow, document constraints and isolate provider-specific logic behind modular service boundaries.

Commit bespoke integration code to Kliya-controlled repositories and provide handover documentation.

# 3. Workstream & Investment Breakdown

| # | WORKSTREAM | INCLUDED OUTCOME | HOURS | FEE |
| --- | --- | --- | --- | --- |
| 01 | Integration architecture & backend foundation | Shared integration layer, service boundaries, auth/secrets pattern, request orchestration, baseline observability, data-mapping conventions and environment configuration. | 22h | R24,200 |
| 02 | Body Intelligence / body measurement | Integrate one approved measurement provider; map supported body outputs into Kliya’s body profile; persist required data; handle incomplete/failure states; document export/retention limitations. | 28h | R30,800 |
| 03 | Virtual Try-On | Integrate one approved VTO provider into the existing journey; support required user/body and garment inputs; return/display results; isolate provider logic; capture latency/failure/usage information where available. | 28h | R30,800 |
| 04 | Garment / simulation / fit infrastructure | Integrate one approved technically accessible provider; map required body/garment inputs; retrieve machine-readable fit signals where exposed; document asset-preparation, preprocessing and vendor dependencies. | 32h | R35,200 |
| 05 | PointAI validation & lightweight path | Validate commercial/technical access, required inputs and available outputs; implement a lightweight MVP path where access supports it, otherwise provide a documented blocker and exact next action. | 10h | R11,000 |
| 06 | Product ingestion / Garment Intelligence | Support approved product inputs including URL/image/size chart/measurements/fabric/manual data; normalise into a common garment structure; retain data provenance; maintain fallback when retailer extraction is unreliable. | 27h | R29,700 |
| 07 | Affiliate commerce / creator attribution | Implement one approved MVP affiliate network (Impact or CJ); support approved account model, link generation and available attribution/commission mapping; structure the interface so another network can be added later. | 25h | R27,500 |
| 08 | QA, security hardening, documentation & handover | Cross-workstream testing, failure-path validation, basic usage/cost visibility, sensitive-data handling checks, technical documentation, known-limitations register, handover and final acceptance support. | 37h | R40,700 |
| ESTIMATED LABOUR BASIS |  |  | 209h | R229,900 |

IMPORTANT WORKSTREAM ASSUMPTION The R230,000 fixed fee is the commercially rounded project price for the 209-hour estimate. It reflects the revised integration-only brief and excludes the broader full-product build. The estimate assumes one selected/approved provider per primary integration workstream and one primary affiliate network for MVP implementation. Multiple providers in the same category, a second affiliate network, bespoke vendor workarounds or proprietary model development require a written change request.

# 4. Delivery Approach & Timeline

Foundation & access: confirm Kliya repositories, environments, credentials, data structures and selected providers.

Core integrations: implement Body Intelligence, VTO and approved garment/simulation pathways.

Data & commerce: implement product ingestion / Garment Intelligence and the approved affiliate network.

Hardening: validate errors, retries, fallbacks, logging, sensitive-data handling and environment configuration.

Acceptance & handover: complete technical validation, documentation, source-code handover and open-item register.

Estimated active delivery window: 8–10 weeks. Calendar timing may extend where Kliya or a third-party vendor has not supplied credentials, commercial approval, licensing, technical documentation, test data or other access required to proceed.

# 5. Client Dependencies

Access to the existing Kliya codebase, relevant backend/database structures and development/test environments.

Selection and approval of the provider to be implemented in each workstream.

Vendor accounts, API/SDK credentials, licences, documentation and test/sandbox access.

A nominated Kliya decision-maker able to approve technical questions and workstream acceptance.

Timely product/domain clarification where Kliya-specific data structures or business rules affect integration mapping.

# 6. Explicit Exclusions

Rebuilding the Kliya MVP or redesigning product journeys/UI.

Building proprietary body-scanning, garment-reconstruction, cloth-physics or specialist simulation engines.

Production-scale/high-availability infrastructure or international rollout optimisation.

Full production-scale retailer integrations or large speculative R&D workstreams.

Automated creator payout, settlement, withholding/tax or marketplace payment infrastructure.

Third-party API, SDK, licensing, cloud, hosting, usage, vendor onboarding or commercial fees.

Any work outside the approved brief unless documented in a written change request.

# 7. Payment Schedule

| MILESTONE | TRIGGER | % | AMOUNT |
| --- | --- | --- | --- |
| Commencement deposit | Agreement signed; before engineering starts | 50% | R115,000 |
| Integration midpoint | Core integration foundation + first accepted workstreams | 30% | R69,000 |
| Final acceptance & handover | Before final source/documentation handover | 20% | R46,000 |

The commencement deposit is non-refundable once project work has started, except where required by applicable law or expressly agreed in writing. Out-of-scope work is R1,100/hour and will only be performed after written approval.

# 8. Project Parameters

| CLICKUP | ClickUp will be used as the client-facing operational record for tasks, milestones, blockers, review notes and delivery evidence. Workstream progress may include time logging for delivery visibility, but the R230,000 engagement is a fixed-scope project fee rather than time-and-materials billing. Commercial changes still require written approval/change control. |
| --- | --- |
| ACCEPTANCE | Each milestone/workstream is reviewed against the agreed scope and acceptance criteria. Written non-conformance feedback should identify the specific requirement not met. |
| THIRD PARTIES | Daybreak is responsible for competent implementation of accessible approved integrations, but cannot guarantee vendor approval, uptime, undocumented capabilities or access that the vendor does not provide. |
| OWNERSHIP | Bespoke project code and final deliverables transfer to Kliya after full payment. Daybreak retains ownership of pre-existing tools, generic methods, know-how and reusable non-client-specific components. |
| VALIDITY | This proposal remains valid until 25 September 2026. |

# 9. Next Steps

01  Approve this revised proposal.

02  Complete and sign the Daybreak Services Agreement.

03  Pay the commencement deposit.

04  Provide repository/environment/vendor access and confirm the selected providers.

05  Daybreak opens the ClickUp delivery workspace and begins the integration foundation.

| KLIYA / CLIENT | DAYBREAK |
| --- | --- |
| Name / capacity: __________________________________ | Name / capacity: __________________________________ |
| Signature: __________________________________ | Signature: __________________________________ |
| Date: __________________________________ | Date: __________________________________ |